## Sheet1
Issue# | Issue Type | Summary | Assumptions/Remarks | Estimate
| Epic-1 | Developer Workstation Setup
| Story-1 | I, as a developer who is using a Abbott provided Windows OS laptop, can virtualize my host OS (i.e. Windows) to run Ubuntu Linux and setup Docker runtime in it
| Story-2 | I, as a developer who is using Abbott provided VDI environment, have my desktop setup to run Ubuntu Linux with Docker runtime in it
| Story-3 | I, as a developer, can download a Magento Starter project from Abbott hosted source code repository. This project will be the latest version of Magento EE, and Abbott approved Magento modules such as Avalara, Fedex, Cybersource etc.
| Story-4 | I, as a developer, can use Docker compose file which came with starter project, to download a docker image from Abbott hosted Docker registry and setup the local-dev environment as my Magento instance. This docker image should contain various docker services to run Magento in my local Docker runtime
| Story-5 | I, as a developer, can use my locally deployed IDE such as PHPStorm to make changes to the Started project. My changes should reflect/updated in my local-dev environment immidiately.
| Story-6 | I, as a developer, have access to the Abbott's PHP and Magento coding standards for me to reference and develop the software
| Story-7 | I, as a developer, have full user/developer guide on Confluence. The guide should provide help content to setup my local environment, how to integrate and leverage the source code repository, how to … (many details to go here)
| Epic-2 | Dev-Ops Tool Chain Setup | Assuming the project to be a medium complexity Java application
| Story-8 | I, as a project, will have 3 Server-dev, 2 Server-int, 1 server-qa and 1 server-prd environments preconfigured to support my various SLC activities (similar setup in code repo?) - Purpose of Server-dev is to allow developer/module team to test their changes onto server side - Purpose of Server-int is to allow entire project to test their changes onto server side (full integration) - Server-qa is to support SQA activities - Server-prd is for production - Server-prd-fix is for production defect replication and fixing | The server creation and deployment will be automated as a part of devops activity. Creating and setting up code in dev environment will take time. | Server-Dev : 40 Server-Int : 3 Server-qa : 1.5 Server-Prod : 1.5 Total: 46 hrs
| Story-9 | I, as a developer, have access to the user/developer guide for standards on source code repository branching and code management strategy |  | 36 hrs
| Story-10 | I, as a developer, when initiates a pull request from my local, will have my request reviewed by the project Architect and one other reviewer before it get merged into the “active” branch |  | 18 hrs
| Story-11 | I, as a developer, will have my code and project reviewed after the code merge into "active" branch using varius pre and post Git hooks such as PHPCodeSniffer, SONARQube for auto code reviews, coding standards compliance checks, OWASP standards, etc |  | 20 hrs
| Story-12 | I, as a developer, will have my code deployed on to Server-dev, Server-int and Server-qa environment upon Successful code merge. Production deployment will be triggered manually. Unsuccessful code merge will result into code fix and initiating a pull request again. (it will not be logged as a defect/bug in JIRA i.e. no ticket for this. |  | 24 hrs
| Story-13 | I, as a developer, will have an automation testing framework to write various auto test cases to be executed before every deployment. The framework should produce a test report which is accessible remotely. The testing framework should support behavior-driven development (BDD) style. Cucumber and Selenium (selenium grid from toolchain) will be used. | Provided automation framework and Test integration with JIRA is in place | 48 hrs
| Story-14 | I, as a developer, will have my code tested automatically (after successful deployment) on server-int and server-qa environment. I will have option to selectivelly run a number of automated test cases on server-dev environment |  | 36 hrs
| Story-15 | I, as a developer, has a recommendation/manual/tools guidance to deploy code on to server-prd-fix environment | Aussuming the complexity is medium and as a stand alone application with no integraion to allied apps | 72 hrs
| Story-16 | I as a developer, will have my code deployement rolled back from all environments (server-dev, server-int and server-qa) when automated testing fails. There will NOT be a JIRA ticket opened for these test case failures |  | 28 hrs
| Story-17 | I as a develper, will have an option to manually trigger sanity/smoke tests cases in Server-prd and Server-prd-fix environment. Performance (using JMeter) and Security scans (using Qualys or AWS Inspector) can also be executed on-demand. Actual transactions should not be logged in the system when executing tests in Production environment | Assuming all the toolchains are integrated | 72 hrs
| Story-18 | I, as a developer, will have Docker images created by automation/build software (Jenkin) and stored in Abbott's artifactory (Jfrog) for future reuse. Deployments into server-qa and server-prd will always be done from the Docker images pulled from artifcatory. |  | 36 hrs
| Story-19 | The build server will also create various tags in Toolchain to support upcoming releases and handle the issues with current release |  | 48 hrs
| Story-20 | I, as a developer, will have option to get Notifications sent to designated emails upon successful deployment, unsuccessful deployments i.e. all events | Assuming no infra issues are in deployment or notification servers | 8 hrs
| Epic-3 | Server side infrastructure design and build
| Story-22 | I, as a Operational Engineer, will have a detailed design and architecture diagram for Radiant infrastructure with following requirements - - AWS N+2 resiliency environment will be built across three availability zones - A single AWS environment will serve all production and non-production instances across the projects (more on this design in Hosting Architecture section) - AWS instances will be auto-scale instances - Auto-scaling will be two layered – a. EKS starting new Pods if instance has capacity b. EC2 instances scaling out and then EKS start new Pods - Since we will use EKS and Pods (Containers) to run the software, there won’t be need of multiple EC2 instances. - The EC2 instances will be sized according to current known demand with some additional capacity to support special events - Amazon services which will be used are – AWS Cloudfront, WAF, Clav Antivirus, Route53, ALBs, Service Managers, RDS and EFS. NagiOS and OSSEC will be used. (More design discussion on it required) - Management servers will be run on their own EC2 instances. TBD – can Management servers also run in containers? - Each Availability zone will have single VPC to host the AWS components
| Story-23 | I, as a Operational Engineer, will have Terraform and Ansible (IaC) scripts to build and maintain the AWS infrastructure components across all zones
| Story-24 | I, as a Operational Engineer, can maintain IaC scripts in a separate source code management (BitBucket) project meant for Project Radiant's IaC code
| Story-25 | I, as a Operational Engineer, have access to clearly defined strategy for source code management for IaC scripts of Project Radiant. Terraform scripts will store states remotely of the managed infrastructure and configuration in BitBucket
| Story-26 | I, as a Operational Engineer, will have access to written, detailed operational RACI matrix for infrastructure build and maintenance in future
| Epic-4 | Application hosting environment architecture design and build
| Story-27 | I, as a Operational Engineer, will have a detailed design and architecture diagram for Radiant's application hosting details with following requirements - - Project radiant will follow develop once and run everywhere principle - Amazon EKS will be used as control plane for the cluster - Instead of AWS ECR project radiant will use JFrog as container image repository - Amazon Linux 2 AMI will be used to serve as the base image for Amazon EKS worker nodes. The AMI is configured to work with Amazon EKS out of the box, and it includes Docker, kubelet, and the AWS IAM Authenticator - Docker will be used as container runtime - It will be a true multitenant environment supporting running various projects simultaneously - Calico on Amazon EKS will be used for network policy enforcement. It will implement network segmentation and tenant isolation
| Story-28 | I, as a Operational Engineer, will have clear design decisions on: shall we add various environment in single segment? Dev, Int, QA, Prod etc. Name space configuration allows resource quota allocation/restrictions. The configuration will allow coexistence of different Magento versions run at the same time. Every Pod will have its own namespace for logical separation. Labels will be used to mark resources for project/teams
| Story-29 | I, as a Operational Engineer, will have IaC scripts to build and maintain the application hosting environment
| Story-30 | I, as a Operational Engineer, will have access to written, detailed operational RACI matrix for application hosting and maintenance in future
| Story-31 | I, as a Operational Engineer, have “helm” package manager configured to deploy Magento/other applications into the cluster
| Story-32 | I, as a Operational Engineer, have IAM polices and groups configured for proper authentications and authorizations
| Epic-5 | Release Management
| Story # | To be added
| Epic-6 | Production / Operational Support
| Story # | To be added
| Epic-7 | Disaster Recovery Procedure
| Story # | To be added