## Readme
This document is prepared with the intent to help the the S/O owners (and the ISL/POL as the case may be) to evaluate the Delivery Readiness of their S/O in key stages of Springboard 2.0 framework. The S/O Owner is expected to collaborate with enabling teams, facilitated by the Amplify Core Team, to complete required evaluation and address delivery readiness gaps, if any.
What is an S/O Tier? The Solutions and Offerings in the portfolio are not alike and lie in a spectrum differentiated by complexity, maturity, size and whether it is thoughtware-based or software-based. Given this variation, the framework allows flexibility in the Stage-Gate framework in a few ways: 1. The Solution or Offer could be categorized into Tier 1 (low complexity or thoughtware-based or already monetized in the market) that needs a low touch approach to push towards full “General Availability” or Market Launch 2. The Solution or Offer could be categorized into Tier 2 (high complexity or software-based or needs collaboration from multiple internal or external teams) that needs a high touch approach to push towards full “General Availability” or Market Launch 3. The ‘entry’ into the Framework can be at any Stage, based upon the current state and maturity of the product solution or offering, whereby needing little or no effort to pass a Stage-Gate 4. Within a particular Stage-Gate, the criteria may apply more to Tier 2 over Tier 1

## Delivery Readiness Checklist
SB Phase | Focus Area | Assessment Questions | Response Guide | Detailed Response (requires input) |  | Score | Response RACI |  |  |  |  | Link to Template (where available)
[5 empty] | Rating | Readiness Score (requires input) | R | A | C | I | Applicable to S/O Tier
Define & Plan | Service Definition | How complex is the S/O definition in terms of service, platform or partnership capabilities? | For Example, Cloud Operations offering require full stack resources who can support infrastructure, applications and security areas in delivery and warrant planning ahead of time in terms of skill set development. |  | High (H) - Requires complex capabilities, not currently in place ; Medium (M) - Requires complex capabilities but most of it is in place; Low (L) - Requires multiple capabilities but only some of it is in place; | Medium' | S/O Owner | ISL/POL |  | Core Team | Tier 1 & 2
|  | Experience in Delivery: How many times has this S/O or related services been executed in past ? | # of client projects executed |  | H - Executed multiple clients projects over multiple years; M - Executed in some projects in recent time; L - No real client experience yet | Medium | S/O Owner | ISL/POL |  | Core Team | Tier 1 & 2
|  | What degree of repetability does this S/O have? OR What is level of customization is required to deliver this S/O (reduces repeatability) ? | Evidence of repeatable thoughtware (frameworks, process methodologies, etc.), software tools/accelerator, leverage our own or 3rd party software. Example: Cognizant Value Stream Mapping offering uses VSM tools and Cog9 tools for application assessment |  | H - Repeatability using s/w tools and frameworks, low customization M - Some repeatable frameworks and tools but needs customization; L - Mostly custom services with low framework/tools usage | Medium | S/O Owner | ISL/POL |  | Core Team | Tier 1 & 2
|  | What degree of industry specific Regulatory & Security Compliance does this S/O need ? | Evidence of regyulatory and compliance requirements considered as part of service definition |  | H - Requires significant regulatory and/or security constructs M - Requires some regulatory/security constructs; L -Does not require any regulatory/security constructs | Medium | S/O Owner | ISL/POL |  | Core Team | Tier 1 & 2
Build & Validate | Service Assurance | What solution blueprint and/or technical architecture documents are ready for this solution/offering? | We recommend all S-Os to have a solution overview and/or architecture document that describes its components and interfaces in some detail |  | H - Available and detailed; M - Some basic overview available ; L - Not available | Medium | S/O Owner | ISL/POL | DE | Core Team | Tier 2
|  | What is level of validation on the solution blueprint and/or technical architecture for your solution/offering (via client feedback, architecture reviews, DE inputs etc.)? | For example, offering based on as-a-service model with multi-vendor platform may need a POC/Pilot deployment to ensure viability of implementation. |  | H - Validated with multiple clients with positive feedback; M - validation with few clients with positive feedback; L - Not validated or feedback needs additional work | Medium | S/O Owner | ISL/POL | DE | Core Team | Tier 2
Market Readiness | Delivery Capabilities | Are pursuit accelerators available for the solution/offerings and effectively used for pre-sales/bid teams? | Provide evidence of Industry benchmarks, Market Insights, Value Realization Matrix, Engagement models etc. |  | H - Yes multiple accelerators available and used; M - Some available and used; L - still being developed | Medium | S/O Owner | ISL/POL | DE | Core Team | Tier 1 & 2
|  | What is maturity level of intended commercial and pricing model in the solution/offering? | Outcome, output based, managed services, fixed bid, T&M; pricing on per transaction, per FTE etc. |  | H - Managed service and outcome/output based; M - Project based, Fixed capacity; L - Staff aug, input based | High | S/O Owner | ISL/POL | DE | Core Team | Tier 1 & 2
|  | What is level of industrialization of underlying service delivery and processes? See Delivery Excellence artifacts tab | Required Delivery Excellence have been created for Delivery Methodologies, Service Management processes and identified KPIs to measure outcomes |  | H - Required DE artifacts available; M - Some DE artifacts available; L - Not industrialzed | High | S/O Owner | DE | ISL/POL | Core Team | Tier 2
| People Enablement | Are relevant training programs available develop skills necessary for the solution/offerings? | Are training plans aligned to Cognizant Career Architecture CCA? E.g. Level 1 certification (Sales) in eLearning platform for field team (CDB proposing 5 level 1 certifications for each CP ), Level 2 certification (Practitioner) field team ( CDB proposing 2-5 level 2 certifications for each CSE ), Level 3 certification (Specialist) and completed enablement session for solution architects on pursuit accelerators, pricing and estimation models built for S/O |  | H - Multiple program built as part of CCA for all roles; M - introduced in CCA; L - more bespoke training programs | Medium | S/O Owner | ISL/POL | Academy | Core Team | Tier 1 & 2
|  | Based on your revenue forecast for thiis solution, do you foresee any resourcing risk to meet the demand - either within your BU or in other BUs the solution depends on? | Plans to make trained resources available within the standard time required for ramp-up? |  | H - Very difficult to find resources in time; M - Moderately difficult to ramp up on time; L - Resourcing is not an issue |  | S/O Owner | ISL/POL | HR-TAG | Core Team | Tier 1 & 2
| Platform/Tools used | Do we have relevant Internal tool platforms built and ready for S/O deployment, if required? | For Example: Automation-HiveCenter, Security- Cyber Security, Threat & Vulnerability management offerings are delivered in as-a-service model need them) |  | H - Internal tools available and used extensively; M - Some tools used; L - No tools used | High | S/O Owner | ISL/POL | DE | Core Team | Tier 2
|  | Do we have relevant external partner tool platforms built and ready for S/O deployment, if required by the S/O ? | For Example: Integrations with partners, content / data feeds, software updates from vendors etc. |  | H - External tools available and used extensively; M - Some tools used; L - No tools used |  | S/O Owner | ISL/POL | DE | Core Team | Tier 2
|  | Do we have Delivery/Operations platform configured and ready for S/O deployment, if required by the S/O ? | For Example mainspring..etc... |  | H - Delivery tools configured fully for the S/O; M - Some features configured and used; L - No delivery platforms used |  | S/O Owner | ISL/POL | DE | Core Team | Tier 2
|  | Do we have required Third Party License Agreements and Access controls in place for the platform to start the operations, if required ? |  |  | H - Multiple proprietary and 3rd party tools available for each phase of delivery; M - Some tools used; L - No tools used |  | S/O Owner | ISL/POL | DE | Core Team | Tier 2
| Security | Have security vulnerabilities been fully identified and are there mitigation plans in place? | Evidence of having identified security vulnerabilities & take necessary corrective actions ( Security vulnerability checks ) |  | H - All security vulnerabilities check done and remediation plan in place; M - Security vulnerabilities checks in process; L - No plan | Medium | S/O Owner | ISL/POL | Corporate Security | Core Team | Tier 2
| Legal | Have legal gaps been fully identified and are there mitigation plans in place? | Evidence of having identified legal gaps & take necessary corrective actions |  | H - All legal gaps check done and remediation plan in place; M - Legal gaps checks and mitigation plans in process; L - No plan in place |  | S/O Owner | ISL/POL | Legal | Core Team | Tier 2
Maintain & Evolve (post Delivery Readiness for GA) | BAU & Performance Management | What plans are in place to effectively monitor and act on operating levers in delivery of the solution/offering? | Describe the levers that are most relevant for this S/O for metrics management - pyramid, utilization, shoring, hiring mix, overheads, partner consolidation |  | Qualitiative reponse | Medium | S/O Owner | ISL/POL | BU Head | Core Team | Tier 1 & 2
|  | Have you identified parameters for process compliance, risk management to measure steady state delivery performance? | Describe the levers that are most relevant for this S/O for risk management |  | Qualitiative reponse | Medium | S/O Owner | ISL/POL | BU Head | Core Team | Tier 1 & 2
|  | Do you have mechanism to collect and benchmark the performance against target and against industry standards on quarterly basis and maintain proper version control, if applicable ? | Plans to analyze performance and market metrics related to the S/O |  | Qualitiative reponse | Medium | S/O Owner | ISL/POL | BU Head | Core Team | Tier 1 & 2

## Delivery Excellence Artifacts
Delivery Excellence Collaterals Checklist
Note: Not all Delivery Excellence artifacts are needed for all S/Os for Delivery Readiness check. It may differ based on type of S/O and is applicable mainly for Tier 2 S/Os.
Sr.No. | Delivery Excellence S/O Artifacts | Description | Is this artifact required for the S/O? | Ready? | Template Link
1 | Deliverability Assessment | Develop Deliverability Assessment Framework to assess the Deal Solution and identify risks for mitigation early in the life cycle | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | Yes
2 | Estimation Framework | Build Effort / Size estimation model to be deployed in bid stage, based on Org/Industry standards | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
3 | Processes | Define detail process and metrics framework which covers various phases, activities, deliverables and Golden Samples of mandatory artefacts | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | Yes
4 | Metrics | Define typical SLAs , productivity metrics and industry benchmarks which can be used for estimation or signing up the SLAs during Deal Stage | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
5 | Tools and Accelerators | Identify applicable reusable assets or accelerators to improve productivity and better quality | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
6 | Audit | Develop a comprehensive audit and assessment framework to assess the service maturity and identify key risks & provide recommendations | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
7 | Product and Service Quality Frmework |  | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
8 | Risk Register | Develop Risk Library based on inputs from SMEs and partners to mitigate the key risks in Execution | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No
9 | Contract Gold Standard | Standard SoW in conjuction with CLRM team | <Yes if required for this S/O, No otherwise. Consult Delivery Excellence ) | No